## Spring 1 (M1)
Not required

## Sprint 2 (M2)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Set Up Git on team's machines | Hunter | Not Started | 0.5
Edit and commit Person 1 class | Hunter | Not Started | 2
Edit and commit Person 2 class | Bhavesh | Not Started | 2
Edit and commit Person 3 class | Stephen | Not Started | 2
Edit and commit Person 4 class | Pranil | Not Started | 2
Edit and commit Person 5 class | Naman | Not Started | 2
Create Build File 1 | Hunter | Not Started | 1
Create Build File 2 | Bhavesh | Not Started | 1
Create Build File 3 | Stephen | Not Started | 1
Create Build File 4 | Pranil | Not Started | 1
Create Build File 5 | Naman | Not Started | 1
Total |  |  | 15.5

## Sprint 3 (M3)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Create Context Diagram | Pranil | Not Started | 1
Brainstorm 10 use cases | Hunter | Not Started | 0.5
Brainstorm 10 use cases | Bhavesh | Not Started | 0.5
Brainstorm 10 use cases | Stephen | Not Started | 0.5
Brainstorm 10 use cases | Pranil | Not Started | 0.5
Brainstorm 10 use cases | Naman | Not Started | 0.5
Collate the best use cases | Hunter | Not Started | 0.5
Create Space Trader FX project (1) | Stephen | Completed | 1 | 0 | 0 | 0
Design Welcome Screen UI (2) | Stephen | Completed | 1.5 | 0 | 0 | 0
Implement pressing "New Game" to access the game configuration dialog (3) | Bhavesh | Not Started | 2
Implement character creation (name + skill points) (4) | Pranil | Not Started | 2
Handle player object creation and game configuration dialog mechanics (5 & 6) | Naman | Not Started | 1.5
Cleanup, readover, code critique | Stephen | Not Started | 2
Total |  |  | 14

## Sprint 4 (M4)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Develop and map out architecture | Hunter | Not Started | 2
Create framework of classes from architecture | Pranil | Not Started | 1.5
Create generators | Bhavesh | Not Started | 2
Create dump abilities | Naman | Not Started | 1.5
Cleanup, readover, code critique | Stephen | Not Started | 2
Total |  |  | 9