## Sheet1
Work Items | Initial Estimate | Adjust Factor | Adjust Estimate | 1 | 2
Team page | 1 | 0.2 | 1.2 | 1.2 | 0
Team contract | 1 | 0.2 | 1.2 | 1.2 | 0
Individual pages | 2.5 | 0 | 2.5 | 2.5 | 0
Get team setup and comfortable with git | 5 | 0.2 | 6 | 6 | 3
Get team setup and comfortable with gradle | 5 | 0.2 | 6 | 6 | 6
Context diagram | 4 | 0.25 | 5 | 5 | 5
Use cases | 5 | 0.25 | 6.25 | 6.25 | 6.25
Initial project setup | 4 | 0.2 | 4.8 | 4.8 | 4.8
Model Classes | 4 | 0.25 | 5 | 5 | 5
UML Domain Model prepared | 6 | 0.2 | 7.2 | 7.2 | 7.2
Implementation of basics | 12 | 0.2 | 14.4 | 14.4 | 14.4
Implementing planets and Universe | 7 | 0.1 | 7.1 | 7.1 | 5
Implementation of MarketPlace | 10 | 1 | 11 | 11 | 8
Implementing ShipYard | 5 | 0.2 | 5.2 | 5.2 | 4
Testing | 8 | 0.3 | 8.3 | 8.3 | 5
UI Evaluation | 5 | 0.4 | 5.4 | 5.4 | 3
Total: | 84.5 | 4.15 | 96.55 | 96.55 | 78.65