## Spring 1 (M1)
Not required

## Sprint 2 (M2)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Set Up Git on team's machines | Hunter | Not Started | 0.5
Edit and commit Person 1 class | Hunter | Not Started | 2
Edit and commit Person 2 class | Bhavesh | Not Started | 2
Edit and commit Person 3 class | Stephen | Not Started | 2
Edit and commit Person 4 class | Pranil | Not Started | 2
Edit and commit Person 5 class | Naman | Not Started | 2
Create Build File 1 | Hunter | Not Started | 1
Create Build File 2 | Bhavesh | Not Started | 1
Create Build File 3 | Stephen | Not Started | 1
Create Build File 4 | Pranil | Not Started | 1
Create Build File 5 | Naman | Not Started | 1
Total |  |  | 15.5

## Sprint 3 (M3)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Create Context Diagram | Pranil | Not Started | 1
Brainstorm 10 use cases | Naman | Completed | 0.5 | 0 | 0 | 0
Collate the best use cases | Hunter | Completed | 0.5 | 0 | 0 | 0
UC1: Start Game | Stephen | Not Started | 1
UC2: Create Character | Hunter | Not Started | 1
UC5: Buy New Goods | Naman | Not Started | 1
UC8: Refuel Ship | Pranil | Completed | 1
UC9: Leave Project | Bhavesh | Not Started | 1 | 0
Create Space Trader FX project (1) | Stephen | Completed | 1 | 0 | 0 | 0
Design Welcome Screen UI (2) | Stephen | Completed | 1.5 | 0 | 0 | 0
Implement pressing "New Game" to access the game configuration dialog (3) | Bhavesh | Completed | 2 | 0
Implement character creation (name + skill points) (4) | Pranil | Completed | 2
Handle player object creation and game configuration dialog mechanics (5 & 6) | Naman | Not Started | 1.5
Cleanup, readover, code critique | Stephen | Not Started | 2
Total |  |  | 17

## Sprint 4 (M4)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Develop and map out architecture | Hunter | Not Started | 2
Create framework of classes from architecture | Pranil | Not Started | 1.5
Create generators | Bhavesh | Not Started | 2
Create dump abilities | Naman | Not Started | 1.5
Cleanup, readover, code critique | Stephen | Not Started | 2
Total |  |  | 9

## Sprint 5 (M5)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Create market screen | Naman | Not Started | 2
Link game screen to market screen | Pranil | Not Started | 1.5
Create ship class to store all relevant data | Bhavesh | Not Started | 2
MarketController (calculating prices and resources) | Stephen | Not Started | 1
MarketController(buying,selling,link controller to front-end) | Hunter | Not Started | 1.5
Add money to player class (add limitation) | Pranil | Not Started | 1
Make individual analysis diagrams | Everyone | Not Started | 1.5
Code review/javadoc | Stephen | Not Started | 1.5
Total |  |  | 9

## Sprint 6 (M6)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Package Diagram/ Trust boundaries | Bhavesh |  | 2
Algorithm for finding planets nearby by fuel and distance | Hunter |  | 2
Encounter with pirates and police | Stephen |  | 2
UI for encounter | Naman |  | 2
UI for nearby planets | Pranil |  | 2
Code review/ Javadoc | Stephen |  | 2

## Sprint 7 (M7)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Class Diagram | Bhavesh
Save/Load State (UI and controller and everything) | Hunter
Random event generation and implementation and extra credit | Naman/ Pranil
Code Critique and Java Doc | Stephen

## Sprint 8 (M8)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Individual sequence diagram | done
Make a ship class with given attributes (similar to resource.java) and shipyard class | Bhavesh, Naman, Pranil
Make a shipyard view and a controller and implement controller with GUI | Sthephen
Code Critique and Java Doc | Hunter

## Spring 9 (M9)
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Method Contracts (individual) | Done
Ensure shipyard available at tech planets/Implement Option to Upgrade Ship | Stephen
Enforce money/slot limits for upgrading ship. Enforce some gadgets only available on higher tech level planet | Naman
Apply design pattern to code | Bhavesh
Code Critique and Java Doc | Hunter